## Slide 1: Salty Groundhogs
Ryan Stavella, Rosemary Bulgarelli, Philip Hasse, Alex Millet, Nick Schwartz, Kevin Lynch

## Slide 2: Decision Required
Status Report - Salty Groundhogs |  |  | 
9/21/2016 |  |  | 
RGY | Item | Description | Mitigation / Help needed
Red |  |  | 
Yellow | Networking Issue | Remote server connectivity issues | contacting system admins
Green | ER Diagram | Complete Entity Relationship diagram with supporting documentation | 
Green | IT Requirements | Gathering requirement for the development of the system | 
Green | Wireframe Mockups | Designing the UI for the HTML web interface | 

## Slide 3: Project Status
Accomplishments
Homework 2
- E-R Diagram
- IT Requirements
Blockers
- Remote Server Connectivity Issues
Activities being worked
- Wireframes
- Researching APIs
- Virtual Servers

## Slide 4: Scope of Project
What it is | What it is not
A website | A desktop application
A Life Coach Resource Site | A place for people to go for life coaching
A secure database | An open repository for customer information
Customer Management | Customer Acquisition
A secure cloud environment | Playstation network (PSN)

## Slide 5: Project Schedule
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Gather Requirements |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Use Cases/ UML |  |  | Final UML |  |  |  |  |  |  |  |  | 
 |  | Create Data Dictionary | Database |  |  |  | 
 |  | Create Github |  |  |  |  |  |  |  |  |  |  |  | 
 |  | ER Diagram |  |  |  |  |  |  |  |  |  |  | 
 |  | IT Requirements |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | HTML |  |  |  |  |  |  | 
 |  |  | Wireframe |  |  |  |  |  |  |  |  |  | 
 |  |  |  | TBD with more project info
 |  |  |  |  | PHP |  |  |  |  |  |  | 

## Slide 6: Project Risks
Risk | Score | Mitigation
Customer data could be lost due to security vulnerability | High | Ensure latest fixes are installed Monitor open source community Extensive testing
Failure to connect to server | Low | Go to server lecture
DB creation and implementation | Mid | normalization
SQL injection | Mid | Sanitizing SQL
SSH Connectivity | Low | Contacting System Admins

## Slide 7: Project issues
Issue | Owner | Action Plan | Checkpoint Date
SSH Connectivity | IT | Contact System Admins | 9/21/2016 Resolved on 9/20/2016

## Slide 8: Lessons Learned
Lessons Learned | Corrective Action / Recommendation
VMware | Workshop

## Slide 9: Communication Matrix
Stakeholder Name | Title | Information Required | Timing / Frequency | Delivery Method | Owner
True Course | Owner | Life Coach Application | Beginning Middle End | PDF/ Pablo | Pablo Rivas
Pablo Rivas | Intermediary Project Director | Progress Reports | Weekly | PDF via Github In class/ In person Email Phone | Kevin, Alex
Salty Groundhogs | Project Team | User Requirements/ Feedback IT Requirements/ Feedback | Multiple Times Per Week | Email Slack | Kevin, Alex
Marist Professors | SME | Project Problems | As needed | Email Office Hours Class | All
Dan and Jimmy | VM Technicians | VM Problems | As needed | Text Email Phone In Person | Kevin, Ryan